## Site Emails
Date | From / Participants | Subject | Site(s) | Category | WO / Ref # | Key Dates | Status / Next Action | Contents | Gmail link
2026-06-24 | Steve Maloney (SolRiver) ↔ Ayaz Kiani (Carolina Solar Services) | CSS / SolRiver O&M — DC wire theft | Elk Solar (Raeford, NC) | O&M / Theft | — | First theft 5/27/26; ongoing | CSS site visit ~6/26 for DC-wire replacement quote; fence-repair quote pending | DC string wire stolen across the array (~100 runs); of 43 inverters only ~10 online. Fencing also stolen/damaged. SolRiver requested urgent CSS site visit + repair quote and sent theft photos, as-builts, and AlsoEnergy screenshots. CSS developing a dispatch plan. | Open thread
2026-06-24 | Steve Maloney / Abhinav Korni (SolRiver) ↔ Jayme Orrock (NARENCO) | SR/NRCO — Elk Inverters Offline / Not Communicating | Elk Solar (Raeford, NC) | O&M / Theft | — | Pad 1 down by 6/12; 35/43 off 6/18; 3 op. 6/23 | NARENCO truck rolls 'non-covered' until fence repaired; overnight patrol being hired | Inverters offline from DC-wire theft: 35 of 43 offline by 6/18, ~10 online 6/22, only 3 operational morning of 6/23; 47 rows vandalized. NARENCO techs dispatched 5/28–6/23 restored some strings. Gate code provided to techs. | Open thread
2026-06-24 | Steve Maloney (SolRiver) ↔ George Porter (Investigate NC) | Site security / overnight patrol | Elk Solar (547 McLaughlin Rd, Raeford, Hoke Co. NC) | Security | — | Site assessment 6/11; redline 6/24 | Contract (in name of Elk Solar LLC, signed by CEO B. Conard) in redline 6/24; start date TBD | Security procurement after repeated theft. Investigate NC did a 6/11 assessment (drone, perimeter, sheriff reports) and proposed 24/7 guard; SolRiver scoped to overnight only (8pm–6am), short-term, terminable at will. | Open thread
2026-06-23 | omops via Projects (NARENCO / NCC) | NARENCO O&M ¦ 06/23/26 Incident Report | Washington Solar; Whitetail | Grid / Utility | WO 50396; WO 50397 | 6/22–6/23 | Restored remotely by NCC; no action | Utility-caused trips. WO 50396 Washington: tripped 6/22 19:21, restored 6/23 09:00. WO 50397 Whitetail: tripped 6/23 15:15, restored 6/23 15:45. | Open thread
2026-06-19 | omops via Projects (NARENCO / NCC) | NARENCO O&M ¦ 06/19/26 Incident Report | Elk; Sunflower; Williams Solar | Grid / Utility | WO 50379; 50380; 50381 | 6/18–6/19 | Restored remotely by NCC; no action | Utility trips restored remotely. WO 50379 Elk: 6/18 19:45 → 6/19 07:15. WO 50380 Sunflower: 6/18 20:30 → 6/19 07:15. WO 50381 Williams: 6/18 20:30 → 6/19 07:15. | Open thread
2026-06-17 | omops via Projects (NARENCO / NCC) | NARENCO O&M ¦ 06/17/26 Incident Report | Whitetail | Grid / Utility | WO 50366 | 6/17 | Restored remotely by NCC; no action | WO 50366 Whitetail: site tripped offline 6/17 04:30; production restored remotely by NCC 6/17 08:30. | Open thread
2026-06-17 | Steve Maloney (SolRiver) ↔ Brenna Franzman (Casey Electric) | Whitetail DAS / fiber review | Whitetail (Tell City / Danville, IN) | DAS / Comms | — | Site visit + calls 6/11–6/24 | Casey recommends full DAS replacement; repair-vs-replace decision pending | Field DAS doesn't match drawings: missing fiber between cabinets, no cell modem, unterminated/unlabeled wiring; Solectria XGI 1500 inverters (need VPN). Casey recommends replacing the DAS rather than tracing it. Also discussing Solectria thermal/neutral-conductor inverter failures and a Padcom float-controller fix. | Open thread
2026-06-19 | Steve Maloney (SolRiver) ↔ Ken Wilson / Ben Furrer (Sargent Electric) | SolRiver Capital Danville IN DAS Rework | Whitetail / Danville, IN | DAS / Comms | — | Proposal 6/16; revised T&M 6/19 | Sargent needs a PO before scheduling; earliest tech ~Mon 6/29 | Sargent to assess installed DAS vs plan sets. Proposal sent 6/16, revised T&M scope 6/19. No work performed yet. | Open thread
2026-06-16 | Steve Maloney (SolRiver) ↔ Jack Stringer (Stem / AlsoEnergy) | DAS modem / cell-plan BOM | Whitetail | DAS / Comms | — | 6/15–6/16 | Needs PO / signed quote to assign a PM | Stem proposed adding a modem/cell plan (with VPN) to the main DAS (WT200) + exterior antenna; flags the Solectria gateway may not fit the AlsoEnergy enclosure. Quote includes ~12 hrs PM + remote re-commissioning of the DAS units. | Open thread
2026-06-17 | Steve Maloney (SolRiver) ↔ Chuck 'Charllie' Joyce (Hendricks Power Coop) | Transformer spec sheets | Whitetail / Danville, IN | O&M / Equipment | 2,500 kVA 3-ph xfmrs | 6/16–6/17 | Specs + nameplate photos received; closed | SolRiver was missing technical specs for installed transformers. Hendricks Power supplied the spec sheet (standard 2,500 kVA 3-phase distribution transformers) plus nameplate photos for each installed unit. | Open thread
2026-06-16 | Bryan Focht / Alix Lefler (Portland General Electric) ↔ John Brown / Riley Sullivan (SolRiver) | Wallace Solar: Allowed to operate at full capacity | Wallace Solar (6475 Wallace Rd NW, Salem, OR) | Grid / Utility | — | Orig. test Mar 2025; revived 6/16 | Provide PGE a contact + remote SEL-relay access for diagnostics | Older PGE thread (Mar 2025 MBTT/transfer-trip test cleared the site to full capacity) revived 6/16; PGE's Bryan Focht is locating the right contact and asking whether SolRiver has remote access to the on-site SEL relay to aid diagnostics. | Open thread
2026-06-15 | Steve Maloney (SolRiver) ↔ Jayme Orrock (NARENCO); memo from Trent Miller (Duke Energy) | Elk Solar — Smart Inverter Pilot — Need Volt-VAR Enabled | Elk Solar (Duke territory, NC) | Grid / Utility | Duke Smart Inverter Pilot | Duke memo 6/8; SR follow-up 6/15 | NARENCO engaging Aderis to re-enable volt-VAR/volt-Watt | After Elk returned to normal circuit arrangement and the 2 MW limit was removed, volt-VAR/volt-Watt is not enabled, causing over-voltage from reactive-power under-absorption (site may still be in constant power-factor mode). Duke requests re-enabling volt-VAR/volt-Watt. | Open thread
2026-06-16 | Duke Energy — Grid Integration / Generator Testing & Performance (GTP); fwd internally by B. Conard / R. Sullivan | Duke Energy Memorandum: IEEE 1547-2018 Compliance — Ride-Through Settings Implementation | All Duke-interconnected SolRiver DER (NC) | Grid / Utility | Memo PDF (fwds: 19ed1081…, 19ed24da…) | Compliance deadline 7/1/2027 | Long-term task: update site voltage/freq ride-through settings on POI reclosers | Duke is updating voltage/frequency ride-through on utility-owned POI reclosers and requires all DER customers to update their own site settings to match for IEEE 1547-2018 compliance by 7/1/2027. Duke will send per-facility reminders as each POI recloser is updated. Brandon flagged it for the long-term task list. Specific setting values are in the attached PDF. | Open thread
2026-06-30 | Tracy Beaudoin (Travelers) / Abhinav Korni (SolRiver) / Dawn Cruz (Marsh) | Solar loss at Graham Project | C&B Graham Energy | Insurance | Claim# F7Q1033; Marsh# 26NYC590490; DOL 2/15/26 | Loss 2/15/26; follow-up 6/10; reply 6/15 | Travelers (Tracy Beaudoin) followed up 6/30 for the Root Cause Report + supporting docs (O&M reports, alarm logs, WOs, Solectria comms, warranty). RCA still in progress / not submitted. | Equipment-loss claim (DOL 2/15/26) involving Solectria inverters. Travelers requested pre-incident O&M reports, alarm logs, work orders, all Solectria communications, warranty/claims docs, and a root cause report. Abhinav replied 6/15 the RCA is not yet finalized. | Open thread
2026-06-16 | Steve Maloney / Brandon Conard (SolRiver) ↔ Ralph Lewis (landowner) | Green Solar CUP citation (water / screening) | Green Solar | Land / County / Tax | County CUP citation | Hearing scheduled then cancelled | Resolving water-availability + screening with county; ongoing | County conditional-use-permit citation. Site is non-irrigated with no domestic water on-site; landowner offered his own supply ~1,000 ft away / a neighbor. Fence screening considered to satisfy the county (ties to Konisto CO). County hearing cancelled; SolRiver actively resolving. | Open thread
2026-06-17 | Steve Maloney (SolRiver) ↔ Michael Jackson (Konisto) | Green — fence screening change order | Green Solar / Green Elementary | Land / County / Tax | Change order (amount in thread) | 2–4 wk lead from approval | Pending county approval; Konisto will NOT warranty the work | Fence-screening change order: screening fabric on 400 ft of fence line north of the entrance, with wind-relief holes recommended. 2–4 weeks to procure/install once approved. | Open thread
2026-06-30 | Bette Anne Mellentine (NARENCO) → SolRiver (Conard, Maloney, projects@) | Richmond Cadle Pay App #12 — Final | Richmond (Richmond County S2, GA) | Construction | Pay App #12 (final) | Final completion 6/24; final inspection 6/22 | NARENCO submitted the full final closeout pkg (Pay App #12 + Final Lien Waiver, FC Cert, GA EPD NOT, Final Inspection, Stormwater NOT). SolRiver acknowledged 6/30 — reviewing; will return signed FC cert and authorize final payment barring questions. | NARENCO submitted the final closeout: Pay App #12 with Final Lien Waiver, Final Completion Certificate (6/24/26), email to GA EPD for NOT submission, and Final Inspection Letter. Indicates project final completion. | Open thread
2026-06-12 | Steve Maloney (organizer); Sargent (Wilson, Friday, Guess); SolRiver (Korni, Conard, Jones) | Invitation: SolRiver/Sargent — Indiana DAS call | Whitetail / Indiana | DAS / Comms | — | Call 6/12 3:00 pm MDT | Coordination call held; feeds the DAS-rework effort | 30-minute DAS coordination call between SolRiver and Sargent Electric regarding the Indiana site DAS rework (calendar invite / meet link). | Open thread
2026-06-15 | Ken Wilson (Sargent Electric) ↔ Steve Maloney | Follow-up — Indiana DAS | Whitetail / Indiana | DAS / Comms | — | 6/15 | Scheduling the Indiana DAS discussion | Sargent following up to schedule the Indiana DAS discussion (same DAS-rework effort). | Open thread
2026-06-24 | Abhinav Korni (SolRiver) → M-RETS admin | M-RETS — Request to Correct Reporting Period End Dates | Shorthorn (M15837); Washington Solar (M17730) | Regulatory / REC | Gen M15837, M17730 | 6/24 | Requested M-RETS correct end dates; awaiting process | Shorthorn shown 1/6–2/2/26 should be 1/6–2/3/26; Washington shown 2/1–3/28/26 should be 2/1–2/28/26. Affects REC reporting accuracy. | Open thread
2026-06-15 | M-RETS (systemadmin) → John Brown (SolRiver) | M-RETS — Issuance Report (Elk Solar) | Elk Solar (Gen M16408, NC) | Regulatory / REC | M16408; 415 (Apr) + 752 (May) RECs | Vintages 04/2026 & 05/2026; issued 6/15 | Issued to SolRiver 'Default' account; informational | M-RETS issued Elk Solar RECs: 415 for the April 2026 vintage and 752 for the May 2026 vintage, into SolRiver Capital, LLC (MM2265). | Open thread
2026-06-15 | PJM-EIS GATS (auto) → projects@ | PJM-EIS GATS — Acct#41498 — Gallipolis Solar River LLC — Generation | Gallia Academy (Gallipolis, OH) | Regulatory / REC | NON217675; Acct#41498; 51,691 kWh | May 2026; entered 6/15 | Logged in GATS; informational | GATS confirmation that 51,691 kWh of May 2026 solar generation was added for the Gallia Academy unit (Meter #1 26,065 kWh + Meter #2 25,626 kWh, both read 05/31/2026). | Open thread
2026-06-30 | Wendy Garduno (SolRiver) ↔ Jack MacMaster (Nelson Mullins); county: R. Fisher, D. Crumley | Re: Bulloch County Assessment Appeals | Bulloch 1A & 1B (Bulloch Co., GA) | Land / County / Tax | FMV $6.8M (audit) vs $2.7M (notices); appeal ack 6/1 | Appeals received by county 5/21; notices dated 5/22; ack 6/1; certified assessment due 7/15; FMV audit ~$6.8M/site vs notice ~$2.7M/site | Counsel (Jack MacMaster, Nelson Mullins) asked Wendy (6/30) for proof the 5/21 appeal was received by the county, ahead of the 7/15 certified-assessment deadline. | Conflicting valuations: the April audit pegged each site at ~$6.8M FMV while May notices show ~$2.7M each. Income-method argument (favored by SolRiver) apparently not addressed in the re-assessment. County confirmed the audit wave targeted solar projects. | Open thread
2026-06-18 | Wendy Garduno (SolRiver) → Alex Krone (Live Oak Bank) | Re: Gallipolis Solar River Q1 2026 Financials and Production | Gallia Academy (Gallipolis, OH) | Regulatory / REC | Q1 2026 lender report | Q1 2026 (Jan–Mar) | Report delivered; implement winter snow-management plan | Live Oak Bank requested Q1 2026 financials + production for Gallipolis. Wendy explained Jan/Feb production was lowered by heavy snow cover and the team will implement a snow management plan for winter. | Open thread
2026-06-18 | Georgia Power (do-not-reply) → projects@ | Outage New — 92 Ben-Hill Rd | GA site (92 Ben-Hill Rd) | Grid / Utility | — | 6/18 7:41 PM; no ETA | Automated outage notice; monitor | Georgia Power reported widespread outages affecting 92 Ben-Hill Rd with no estimated restoration time. | Open thread
2026-06-13 | Georgia Power (do-not-reply) → projects@ | Outage New — 2436 GA-Hwy-88 | GA site (2436 GA-Hwy-88) | Grid / Utility | — | 6/13 2:48 PM; restore ~5:00 PM | Automated outage notice; monitor | Georgia Power reported an outage at 2436 GA-Highway-88 with anticipated restoration by 06/13 05:00 PM. | Open thread
2026-06-22 | Steve Maloney / Brandon Conard (SolRiver) ↔ Oregon CSP (J. Siegel, M. Larson) / Energy Solutions (S. Lauer) | Re: Annual Reconciliation Notice (oversubscription fee) | Oregon CSP / Canyonville Solar (OR) | Regulatory / REC | $15,247.38; OR PUC Order 26-180 | Method eff 5/27; response due 6/19; deferred to 7/8 billing | PA rejected lump-sum redistribution; SolRiver to find another method | New OR PUC reconciliation requires oversubscribed participants to repay the utility. SolRiver chose to cover the fees and proposed a single $15,247.38 payment for redistribution, but the PA said it can't redistribute lump-sum funds, so the mechanism was rejected. | Open thread
2026-06-02 | Wendy Garduno (SolRiver) ↔ Lisa Hawley (Douglas County, OR planner) | Fwd: SR/Douglas County — Canyonville Solar | Canyonville Solar (N. Gazley Rd, Myrtle Creek, OR) | Land / County / Tax | Approval Condition #4 (decommissioning MOU) | Permit extension ~3/25; MOU drafting Jun | Provide entity/signer details so county can draft the MOU | To satisfy Condition #4, the county wants a decommissioning MOU (modeled on a Linn County agreement). SolRiver provided the decommissioning report/site plan; the county needs corporate name, ATTN, address, email, and authorized signer to draft the MOU. | Open thread
2026-06-17 | Oregon CSP (M. Larson) → skylar@ (former); fwd by B. Conard | Fwd: Certification Deadline Approaching — Canyonville 1 and 2 | Canyonville Solar 1 & 2 (OR) | Regulatory / REC | Ticket 15663:1176751 | Certification deadline 6/26/2026 | Draft extension request (4 required points) or certify before 6/26 | OR CSP warned that Canyonville 1 & 2's certification deadline (6/26) is near and laid out extension-letter requirements. Brandon directed the team to start drafting a response. | Open thread
2026-06-18 | Donna DuRant Winchester (landowner) ↔ Steve Maloney (SolRiver) | SC Property Tax return — DuRant Farm Solar (Timmonsville, SC) | DuRant Farm Solar (Timmonsville, SC) | Land / County / Tax | SC DOR PT-300 | SolRiver filed PT-300 Feb 2026 | Confirm to landowner; resolve possible filing disconnect | Landowner forwarded an SC DOR property-tax notice; after speaking with SC DOR she says both landowner and SolRiver must file separately. Steve replied SolRiver already filed its PT-300 in February with no state disputes. | Open thread
2026-06-24 | Vonda Hutchinson (Waynesboro City Public Schools, VA) → Matt La Rocca (SolRiver) | Re: Waynesboro/SolRiver: Renewable Energy Credit Transfers | WCPS — Waynesboro City Public Schools (VA) | Regulatory / REC | Remaining ~20% RECs; via SSA amendment | Thread Jan–Jun; decision 6/24 | Waynesboro agreed if no fee; SolRiver to execute transfer (SSA amendment) | SolRiver held Waynesboro's remaining RECs and proposed amending the SSA so the remaining 20% of RECs (existing + future) transfer to SolRiver. Waynesboro agreed provided there is no fee to them. | Open thread
2026-06-25 | Steve Maloney (SolRiver) ↔ Tom Shanahan (Solectria); Solential cc | Graham Solar — Inverter RMA Status Update | C&B Graham Energy | O&M / Equipment | RMA units 4,7,13,17,20,22,23,34,35 | 6/25 opened; Solectria holds 6 units (27,31,3,2,8,9) | Steve asked Solectria (Tom Shanahan) to ship the 2 spare units now; units offline for months awaiting replacements; awaiting RMA ship/delivery dates before PO. | 9 inverters offline (8 thermal, #4 component failure); coordinating RMA replacements with Solectria. | Open thread
2026-06-24 | Steve/Abhinav/Parker (SolRiver); Nikita Sesay (Got Electric) | Fwd: 2026 PMI Report — WCPS William Perry | WCPS — William Perry Elem.; Kate Collins; Westwood Hills; Waynesboro HS (VA) | O&M / Equipment | Inverter 1 (WPES); 2026 PMI PDFs | 6/18 report; 6/24 inverter back online | Got Electric (Nikita) restored WPES Inverter 1 on-site 6/24; Parker to log; tree-trimming quote pending. | 2026 PMI reports delivered for WCPS sites; Inverter 1 (offline since 6/12) restored. | Open thread
2026-06-25 | Steve/Abhinav/Brandon (SolRiver); Ethan Shaw (Solential O&M) | Re: Inverter Failure — WCPS (Solential) | WCPS (Solential-managed, VA) | O&M / Equipment | 9 inverters offline; RMA 7,13,17,22,23,34,35; Inv 4 skyper/IGBT (since 6/9) | 6/23–6/25 | Solential confirms RMAs submitted on discovery; units returned one-at-a-time from Solectria; skyper board (not in spare kit) submitted. SR weighing buying spares. | Root-cause discussion on repeated inverter failures; same Solectria RMA campaign as Graham. | Open thread
2026-06-29 | Steve/Brandon/Riley (SolRiver); Danny Avrith/Judy Briones/Alexa Rich (MaxSolar) | Re: Vegetation Management + PMI — Town of Monroe Solar Farm | Monroe Landfill (NY) | O&M / Equipment | Veg WO #26024; PMI WO #26026; Inv 20 (Insulation Error since 5/30) | Veg mow scheduled 6/29; 6/29 tree fell onto modules | Both WOs approved; CHANGE ORDER pending SR approval to remove fallen tree + finish mowing; assess possible module damage; 1-camera quote being scoped. | Veg management + PMI for Monroe; a tree fell onto modules 6/29 prompting a change order. | Open thread
2026-06-25 | Abhinav/Brandon (SolRiver); Jayme Orrock/Jacob Budd (NARENCO) | SR/NRCO — Whitetail Site Offline | Whitetail (Danville, IN) | O&M / Equipment | 150A AC breaker (RVC, replaced 7/2025, 1-yr warranty) | Offline ~6:45pm 6/14; latest 6/25 | NARENCO recommends NO further repair — insulation resistance in gigaohm range, breaker believed to have operated correctly; wait-and-monitor unless recurs. | Investigated Whitetail trip; concluded breaker functioned correctly on overcurrent, not a defect. | Open thread
2026-06-30 | Abhinav/Steve (SolRiver); Lane Ellison/Jason Sparks (HEP) | Re: Proposals and Followup — Elk field return (HEP) | Elk Solar (Raeford, NC) | O&M / Theft | 43 inverters, 35 offline; ~100 DC runs stolen (~45,000 ft blk + 40,000 ft red); ~700 ft fence | HEP visit offered Wed; SR onsite 6/26; follow-up 6/30 | Awaiting HEP quote for DC-wire replacement (with stock availability/timeline) and fence repair. | HEP asked to return to Elk to scope DC-wire theft repair. | Open thread
2026-06-25 | Abhinav/Steve (SolRiver) → Solar Gladiator | SR/Solar Gladiator — Urgent Inspection & Repair Quote (theft) | Elk Solar (Raeford, NC) | O&M / Security | ~100 DC runs + perimeter fence stolen | Sent 6/25 | Cold outreach for earliest availability + repair quote; no response in thread. | Urgent theft-repair RFQ to a candidate contractor. | Open thread
2026-06-25 | Abhinav/Steve (SolRiver) → Direct Services Group | SR/DSG — Urgent Inspection & Repair Quote (theft) | Elk Solar (Raeford, NC) | O&M / Security | Same theft scope (fence + ~100 DC runs) | Sent 6/25 | Outreach to DSG; awaiting reply. | Urgent theft-repair RFQ. | Open thread
2026-06-25 | Abhinav/Steve (SolRiver) → ACT Power Services | SR/ACT — Urgent Inspection & Repair Quote (theft) | Elk Solar (Raeford, NC) | O&M / Security | Same theft scope (fence + ~100 DC runs) | Sent 6/25 | Outreach to ACT; awaiting reply. | Urgent theft-repair RFQ. | Open thread
2026-06-25 | Steve (SolRiver); Glenn McDonald/Bette Anne Mellentine (NARENCO) | Re: Longleaf Solar Pay App 13 — Final Completion | Longleaf Solar (NC) | Construction | Pay App 13 (Final Completion); signed FC Cert; lien waiver | Pay App 6/11; signed cert 6/25 | Signed Final Completion cert sent; payment approved & processing. | Closeout of Longleaf construction — final completion. | Open thread
2026-06-25 | Brandon/Riley (SolRiver); Merissa Larson (Oregon CSP) | Certification Deadline Extension Request — Canyonville 1 & 2 | Canyonville Solar 1 & 2 (OR) | Regulatory / REC | Pre-cert extension letter | Cert deadline 6/26; letter submitted 6/25 | Extension request submitted to OR-CSP PA; awaiting response. | Requested extension of the OR community-solar certification deadline. | Open thread
2026-06-25 | Abhinav/Steve (SolRiver) → HBIS | SR/HBIS — Fence Repair, Raeford NC | Elk Solar (547 L McLaughlin Rd, Raeford, NC) | O&M / Security | ~700 ft fence + ~10 ft section + man-sized hole | Sent 6/25 | Outreach for interest + quote + start date; awaiting reply. | Fence-repair RFQ to HBIS. | Open thread
2026-06-26 | Abhinav/Steve/Brandon (SolRiver); James (Balado) | SR/Balado — Fence Repair, Raeford NC | Elk Solar (547/265 L McLaughlin Rd, Raeford, NC) | O&M / Security | Temp fence securing (2-person) | 6/26; work requested that weekend | Engaged Balado for emergency temporary securing; asked for hourly rates + helper. | Emergency temporary fence securing at Elk. | Open thread
2026-06-26 | Abhinav/Wendy/Brandon/Steve (SolRiver); Balado | Estimate 1022 from Balado Home Solutions | Elk Solar (Raeford, NC) | O&M / Security | Est 1022: $800.63 (deposit $200.16) | 6/26 | Deposit paid by Brandon on SolRiver card (1001); booked to Elk; Wendy filing SEH reimbursement. | Balado deposit for temporary fence work. | Open thread
2026-06-27 | Abhinav/Brandon/Wendy (SolRiver); Balado | New payment request from Balado — invoice 1025 | Elk Solar (Raeford, NC) | O&M / Security | Inv 1025: $680.53 (balance $480.37) | 6/27 | Balance paid by Brandon. | Balado balance for fence work. | Open thread
2026-06-30 | Abhinav/Steve (SolRiver); Jayme Orrock/Joseph Lang (NARENCO) | SR/NRCO — Bulloch 1B Underperformance | Bulloch 1B (Bulloch Co., GA) | O&M / Equipment | 1B vs 1A; interrow shading noted in 1B PMI | Raised 6/26; NRCO response 6/30 | NARENCO confirmed underperformance; tech onsite; interrow shading a likely (possibly partial) cause — tech to confirm if sole source. | Investigating Bulloch 1B underproduction vs 1A. | Open thread
2026-06-26 | Steve (SolRiver); Zach Patterson/Lane Ellison/Jason Sparks (HEP) | Re: Elk Solar — Camera Installation Quote | Elk Solar (Raeford, NC) | O&M / Security | 4-camera install (Vosker + Unistrut); 2 techs/2 days | HEP proposal 6/1; SR Qs 6/25; HEP reply 6/26 | HEP confirmed scope incl. procurement + install; commissioning via Vosker app; SR reviewing, pending approval; schedulable 1–3 wks from approval. | 4-camera security install quote for Elk. | Open thread
2026-06-24 | projects@ (NARENCO NCC) → Brandon; Jayme/Joseph/Jacob (NARENCO) | NARENCO O&M ¦ 06/24/26 Incident Report | Warbler | Grid / Utility | Ticket #50399 | Offline 6/24 06:42; restored 6/24 08:30 | Restored remotely by NCC; no action. | Utility trip at Warbler; reclosed remotely. | Open thread
2026-06-29 | Steve Maloney (SolRiver) ↔ Jonathan Helmuth (Solectria) | Re: Solectria Quote — 5 spare inverters | C&B Graham Energy (spare inverters) | O&M / Equipment | Quote — 5 spare inverters; PO to Orders@Solectria.com | Quote 6/12; reply 6/29 | Solectria: 4–5 mo lead time; 2 safety-stock units buildable ~1 mo; once PO issued ship ~2/mo with 2 immediate. SR finalizing purchasing decision. | Spare-inverter purchase for Graham; lead-time confirmation. | Open thread
2026-06-29 | Abhinav/Steve/Brandon (SolRiver) ↔ Dawn Cruz (Marsh) | SR/Marsh — Property Insurance & BI Claims — Elk Solar | Elk Solar (Raeford, NC) | Insurance | $25K deductible/occurrence | Claim initiated 6/24; call set Tue 6/30 11:15 MT | Dawn Cruz confirmed 11am MT; kickoff call Tue 6/30 11:15am–12pm MT; police reports + theft photos provided. Kickoff call HELD Tue 6/30 (Gemini meeting notes generated). | Property + business-interruption theft claim for Elk. | Open thread
2026-06-29 | Abhinav Korni (SolRiver) — calendar invite | Invitation: SR/Marsh — Elk Property Insurance & BI Claim | Elk Solar (Raeford, NC) | Insurance | — | Tue 6/30 11:15am–12pm MT (Google Meet) | Calendar invite for the Marsh claim kickoff; guests Steve, Brandon, Parker, om@, Dawn Cruz. | Meeting invite for the insurance call. | Open thread
2026-06-29 | Abhinav Korni (SolRiver) → NARENCO (Jayme Orrock, Joseph Lang, Jacob Budd) | SR/NRCO — Site Trips/Outages on 6/28 | Elk; Warbler; Whitetail (NC) | Grid / Utility | — | Outages 6/28 (all 3 sites, zero production) | Asked NARENCO why all three tripped 6/28 and whether Duke reported a grid event; remote vs onsite reclose; awaiting reply. | All three NC sites showed 6/28 outages per AlsoEnergy. | Open thread
2026-06-29 | NARENCO NCC daily report (via projects@) | NARENCO O&M ¦ 06/29/26 Incident Report | Whitetail; Washington Solar | Grid / Utility | WO 50425 (Whitetail); WO 50429 (Washington) | Whitetail 6/27 19:27→6/28 15:47; Washington 6/29 04:00→09:30 | Restored remotely by NCC; no action. | Utility trips at Whitetail & Washington; reclosed remotely. | Open thread
2026-06-30 | Steve/Abhinav (SolRiver) ↔ Chris Bailey (NC DEQ-DEMLR) | Longleaf & Williams Solar — filing Notice of Termination (NOT) | Longleaf Pine Solar; Williams Solar (NC) | Regulatory / REC | Stormwater/erosion permit NOT | Inquiry 6/16; DEQ 6/18; payment Q 6/29; escalation 6/30 (7/1 late-fee concern) | Invoices paid but NCDEQ portal still shows 'Payment Due'; Steve escalated 6/30 to avoid 7/1 late fees; awaiting Chris Bailey (NCDEQ) guidance before filing the NOT. | Permit closeout (Notice of Termination) for two NC sites. | Open thread
2026-06-29 | SolRiver (Steve, Riley) / Perch (Eric Timlin) / PGE / Arcadia–ORCSP | Arcadia/PGE — Oregon Shines QRE Agreement (Sheridan, Auburn, Wallace) | Sheridan; Auburn; Wallace Solar (OR) | Regulatory / REC | WREGIS W20751 / W20747 / W31252 | Ext 5/29→6/12→6/30; reports filed 6/29 | Perch submitted 2024–25 REC annual reports to ORCSP 6/29; still need countersigned QRE agreement from PGE + QRE fee invoice. | Oregon Shines QRE REC compliance for 3 OR sites. | Open thread
2026-06-29 | Riley/Wendy (SolRiver) → REC Solar, Monarch/Cardinal, Aspen; Bowery, GMASS, Smithmyer, Keystone, BBG | SolRiver — Bulloch County GA appraiser sourcing & peer coordination (9 threads) | Bulloch 1A & 1B (Bulloch Co., GA) | Land / County / Tax | OCGA §48-5-311(f) arbitration; digest yrs 2023–25 | All outreach 6/29 | Sourcing a certified appraiser for the Bulloch tax appeal (non-binding arbitration); emailed peer operators + 5 appraisal firms; BBG (Robert Ryan, MAI) is the only firm to respond so far. | Coordinated appraiser search for the Bulloch tax arbitration (transcripts kept individually). | Open thread
2026-06-30 | NARENCO NCC daily report (via projects@) | NARENCO O&M ¦ 06/30/26 Incident Report | Sunflower; Elk (NC) | Grid / Utility | WO 50435 (Sunflower); WO 50436 (Elk) | Sunflower 6/30 07:00→09:15; Elk 6/27 15:45→6/29 09:00 | Restored remotely by NCC; no action. | Utility trips at Sunflower and Elk; reclosed remotely by NCC. | Open thread
2026-06-30 | Abhinav/Steve/Brandon (SolRiver); Joseph Lang/Jayme Orrock/Andrew Giraldo (NARENCO) | SR/NRCO — Williams Inverter A2 (AC breaker burn-up) | Williams (NC) | O&M / Equipment | Inverters A1 & A2 (Siemens); PMI IR 4/1/26 | A2 tripped 6/27, back online 6/30; both breakers replaced 6/30 | A2 AC breaker burned up (suspected loose/under-torqued lug); its heat melted part of A1's breaker — NARENCO replaced both 6/30. SolRiver pressing for root-cause diagnosis, Siemens opinion, megger/DC-string checks, PMI-doc upload; flagged that a 4/1 PMI IR scan showed hotspots >NETA threshold that were never reported. | Inverter A2 breaker failure at Williams; corrective replacement + root-cause push. | Open thread
2026-06-30 | Steve/Brandon (SolRiver); Jayme Orrock/Glenn McDonald/Joseph Lang (NARENCO) | SR/NRCO — Vegetation overgrowth / mowing (Elk, Longleaf, Sunflower) | Elk; Longleaf; Sunflower (NC) | Land / County / Tax | — | Longleaf complaint ~6/11; Elk request 6/30; Sunflower 7/1 | Landowner complaints of overgrown vegetation; SolRiver asked NARENCO to mow Elk (crew missed road/fence buffers) and Longleaf, and to confirm Sunflower's last mow date. | Vegetation/mowing follow-ups across three NC sites. | Open thread
2026-06-30 | Steve/Brandon (SolRiver); Ty Wyman (Dunn Carney); county | Re: DC/Green Solar — permit violation matter | Green Solar (OR) | Land / County / Tax | County code-enforcement (fence screening) | Citation ~6/15; hearing 6/18; terms 6/26–27; accepted 6/30 | Steve accepts the county settlement terms (annual fence-screening inspection/repair + responsive fixes); will issue a PO to the contractor and schedule the work; awaiting Brandon's comments. | Resolution of the Green Solar fence-screening code-enforcement matter. | Open thread
2026-06-30 | Riley/Steve (SolRiver); Sterling Perry (Duke) | Re: Final Accounting Report — Williams Solar (Duke FAR) | Williams Solar (NC) | Grid / Utility | Solar 008127 / DEP INT-008127TU; Duke ISA 9/3/2020 | Duke FAR 5/27/26; SolRiver rebuttal 6/30 | Riley disputes Duke's FAR cap methodology — argues Williams is covered by the 11/20/2020 Duke–GreenGo bilateral settlement (capped at IA Estimated Cost + exceptions), not the 130% True-Up cap Duke applied. Williams paid $1,126,721.07 (~$100K over IA estimate). Awaiting Duke's response. | Interconnection cost-reconciliation dispute for Williams Solar. | Open thread
2026-06-30 | Shawn Seippel (TMI Electric); Abhinav/Steve/Brandon/Subhadeep (SolRiver) | Re: SR/TMI — Gallia Academy Inverter 2 Offline | Gallia Academy (Gallipolis, OH); Green Elementary | O&M / Equipment | AC-disconnect scope; Inverter 1 comm | Inv 1 offline since 4/6; onsite 6/23–24; Spring PM 6/24; resolved 6/30 | Gallia HS Inverter 1 (comm cable pulled out — likely a mower hit the conduit) re-terminated & back online with production back-filled; Spring PM completed 6/24. AC-disconnect replacement estimates: $21K (HS, 2 failing units) + $13K (Green Elem); awaiting SolRiver go-ahead (~3-wk lead). | Gallia Academy inverter restored; AC-disconnect replacement quotes pending. | Open thread
2026-07-01 | Miller Bros Solar Operations Center (F. Tejeda); Brandon/Steve/om (SolRiver) | 00040817 — RRH 1&2 Site 2 Inverter 10 Offline | RRH 1&2 (Site 2) | O&M / Equipment | WO 00040817 | 7/1 notice | Miller Bros SOC alert — Site 2 Inverter 10 offline/not producing; new condition, no resolution yet. | New inverter-offline alert at RRH 1&2 from the O&M provider. | Open thread
2026-06-30 | NCDEQ DWM (Adam Ulishney; Jessica Montie); Matt La Rocca (SolRiver) | NCDEQ DWM USSP Registrations submitted (8 sites) | Warbler; Washington; Elk; Gray Fox; McLean Homestead; Harding; Williams; Longleaf Pine (NC) | Regulatory / REC | DWM-USSP-1542/1543/1544/1546/1550/1551/1552/1553 | Submitted/received 6/30 | Eight NC solar USSP registrations submitted and received; under DWM review; per-site registration-fee invoice to follow. | Batch NCDEQ solar-facility (USSP) registrations for eight NC sites. | Open thread
2026-06-30 | M-RETS (systemadmin) → projects@ (John Brown) | M-RETS — Issuance Report (Shorthorn & Washington) | Shorthorn (M15837); Washington Solar (M17730) | Regulatory / REC | Gen M15837, M17730 | Issued 6/30 | RECs issued to SolRiver Default account: Shorthorn 02/26=1,144; 03=1,175; 04=1,950; 06=1,972; Washington 02/26=653. Informational. | Routine REC issuance notifications. | Open thread

## Filtered Out (no site)
Date | From / Subject | Category | Note | Gmail link
2026-06-24 | ChatGPT — find products from an image | Ad / Promo | OpenAI marketing | Open thread
2026-06-24 | Altvia — IR event highlights | Newsletter | Vendor newsletter | Open thread
2026-06-24 | Anna Dillbeck — consultant waiting | Recruiter | Staffing outreach | Open thread
2026-06-23 | Verizon 5G Business Internet | Ad / Promo | Telecom marketing | Open thread
2026-06-23 | Nodal — June 2026 newsletter | Newsletter | Market newsletter | Open thread
2026-06-23 | Renewable procurement sessions — register by 6/30 | Ad / Promo | Conference promo | Open thread
2026-06-23 | Fundraising Readiness Checklist | Ad / Promo | Marketing | Open thread
2026-06-23 | Seraphim USA — Domestic Content panels | Vendor | Panel-supply sales | Open thread
2026-06-23 | Simplifile — credit card surcharge change | Admin | Billing notice | Open thread
2026-06-23 | Colorado SoS — Periodic Report (Korsolis LLC) | Admin | Entity filing reminder | Open thread
2026-06-23 | ChatGPT — turn notes into a draft | Ad / Promo | OpenAI marketing | Open thread
2026-06-23 | IDR — expert network invite | Recruiter | Expert-network outreach | Open thread
2026-06-23 | Chicago Title — form 6s | Admin | Title/closing admin | Open thread
2026-06-23 | Film crowdfunding pitch | Ad / Promo | Solicitation | Open thread
2026-06-22 | Privacy Policy update | Admin | Policy notice | Open thread
2026-06-22 | Anna — recruiter intro to Matt | Recruiter | Staffing outreach | Open thread
2026-06-22 | Working capital loan pitch | Ad / Promo | Lending solicitation | Open thread
2026-06-22 | Climatize — idle balances pitch | Ad / Promo | Fintech solicitation | Open thread
2026-06-22 | CJR Renewables — Intersolar invite | Ad / Promo | Event marketing | Open thread
2026-06-18 | EIA 860/923 — contact change (Matt LaRocca) | Regulatory | Reporting-contact admin | Open thread
2026-06-18 | Identity Services — brand protection | Ad / Promo | Marketing | Open thread
2026-06-18 | EIA-860 May report overdue | Regulatory | Filing reminder (fleet-wide) | Open thread
2026-06-18 | PGE business feedback survey | Ad / Promo | Utility survey | Open thread
2026-06-17 | Newsletter — closing faster | Newsletter | Industry newsletter | Open thread
2026-06-17 | PEI — AI webinar | Ad / Promo | Webinar promo | Open thread
2026-06-16 | DEQ / AccessDEQ — password resets & OTP (5 msgs) | Auth | NC DEQ portal auth | Open thread
2026-06-16 | CCEBA — Duke NC IRP court update | Industry | Policy update | Open thread
2026-06-16 | EIA-860 overdue (Matt / Brandon) | Regulatory | Filing reminder | Open thread
2026-06-16 | PR Newswire — media monitoring pitch | Ad / Promo | Sales | Open thread
2026-06-16 | Spencer Ogden — consultant waiting | Recruiter | Staffing outreach | Open thread
2026-06-16 | Oregon CSP — PA compliance extension to 6/30 | Regulatory | Related to Oregon CSP (site sheet) | Open thread
2026-06-15 | FedEx Rewards offers | Ad / Promo | Marketing | Open thread
2026-06-15 | WREGIS — bulletin | Newsletter | Registry newsletter | Open thread
2026-06-15 | CJR Renewables — Intersolar (2 more) | Ad / Promo | Event marketing | Open thread
2026-06-14 | HartEnergy — leadership resources | Newsletter | Industry newsletter | Open thread
2026-06-15 | NC Legislation Committee update | Industry | Policy update | Open thread
2026-06-13 | ChatGPT — what's new | Ad / Promo | OpenAI marketing | Open thread
2026-06-25 | PGE — business feedback survey | Ad / Promo | Utility survey | Open thread
2026-06-25 | Amplify — new product features (PR Newswire) | Ad / Promo | Marketing | Open thread
2026-06-25 | SUPER DUG — executive lineup | Ad / Promo | Conference promo | Open thread
2026-06-25 | 'DUET pinpoints solar losses' — vendor blast | Ad / Promo | Vendor marketing | Open thread
2026-06-25 | Lisa Shpritz (Global Environmental Group) — invoice request Q4'25/Q1'26 | Admin | Billing/doc request | Open thread
2026-06-25 | Green-e — RY25 Verification Review confirmation | Regulatory / REC | Fleet REC admin (no single site) | Open thread
2026-06-25 | Aderis Energy — Acuity report completed | Auto / Report | Automated report delivery | Open thread
2026-06-25 | 'HIGH PRIORITY' — send your texting digit | Spam | Likely phishing — do not reply | Open thread
2026-06-25 | Denver network-diagnostic pitch | Ad / Promo | IT sales solicitation | Open thread
2026-06-26 | Positive Pay System — holiday reminder (UCB Treasury) | Admin / Bank | Treasury notice: bank open Fri 7/3; decide items by 1:30pm ET | Open thread
2026-06-24 | Adobe Acrobat Sign — 'McColl SC PROPOSAL' agreement canceled | Admin / E-sign | Signer declined; exchange canceled — no O&M content | Open thread
2026-06-25 | Wendy Garduno → Enhanced Capital — Purple Aspen Q1 2026 reporting pkg | Financial / Reporting | Tax-equity investor quarterly reporting; no O&M relevance | Open thread
2026-06-25 | Wendy/Glenn Drost → United Community Bank — Purple Aspen Q1 2026 reporting pkg | Financial / Reporting | Lender quarterly + audited financial reporting; no O&M relevance | Open thread
2026-06-27 | Anthropic — 'We'd love your thoughts on Claude' | Survey | Product survey | Open thread
2026-06-27 | Claude — 'Your seat was upgraded' | Ad / Promo | Product notice | Open thread
2026-06-26 | AccessDEQ Payment Receipt | Admin | NCG01/NCG25 annual fee receipt | Open thread
2026-06-26 | Positive Pay System Notifications | Admin | Bank notice | Open thread
2026-06-26 | 'Finding out Too Late' (theft-security pitch) | Ad / Promo | Security vendor marketing | Open thread
2026-06-26 | Fwd: Bluewater Update List — panels & storage | Vendor | Supplier update list | Open thread
2026-06-26 | Asana — 1 overdue task | Notification | Task reminder | Open thread
2026-06-28 | ChatGPT — 'Turn your hook into a caption' | Ad / Promo | OpenAI marketing | Open thread
2026-06-28 | HartEnergy — Energy Leadership Resources | Newsletter | Industry newsletter | Open thread
2026-06-29 | 'Please Advise - Evaluation and Timing' (Cision/Brandwatch) | Vendor | Media-monitoring sales follow-up | Open thread
2026-06-29 | Asana — Monday tasks assigned | Notification | Task digest | Open thread
2026-06-30 | COSSA — 2026 Legislative Recap | Newsletter | Policy newsletter | Open thread
2026-06-30 | Belfry — Weekly Activity Report (Sol River Capital) | Auto / Report | Automated activity report (om@) | Open thread
2026-06-30 | Asana — 'Make Asana the perfect fit' | Ad / Promo | Product marketing | Open thread
2026-06-29 | WREGIS Bulletin | Newsletter | Registry newsletter | Open thread
2026-06-29 | 'for Solriver Capital' — PCBA assembly pitch | Spam | Cold manufacturing solicitation | Open thread
2026-06-29 | Legislative Update from CCEBA | Industry | Policy update | Open thread
2026-06-29 | 'Brandon Conard' / 'Brandon Conard (Managing Partner)' (managementdesk211 / officiallyofficial @gmail) | Spam / Phishing | Likely CEO-impersonation scam targeting Parker — do NOT reply | Open thread
2026-06-29 | Renewable Energy Markets Conferences — unsubscribe confirmation | Admin | List unsubscribe notice | Open thread
2026-06-29 | Duke Energy — DER Alert (recloser status changed, x2) | Auto / Report | Automated recloser alerts (om@) | Open thread
2026-06-29 | California State Lands — Renewable Energy Lease RFP (due 6/30) | Industry / Dev | Land-lease RFP notice (development, not O&M) | Open thread
2026-06-15 | Bluewater — Adani modules / module sourcing (JA, GCL) | Vendor | Module-procurement sourcing (no active O&M) | Open thread
2026-07-01 | COSSA — 2026 Topgolf Networking Event | Ad / Promo | Event promo | Open thread
2026-07-01 | PR Newswire — new account manager (Courtney Libby) | Vendor | Sales intro | Open thread
2026-07-01 | Verizon — 'Power up your business' | Ad / Promo | Telecom marketing | Open thread
2026-07-01 | Seraphim USA — 440–595W modules (LA warehouse) | Vendor | Panel-supply sales | Open thread
2026-07-01 | Belfry — Daily Activity Report | Auto / Report | Automated activity report (om@) | Open thread
2026-07-01 | Asana — 'What's new in Asana' | Ad / Promo | Product newsletter | Open thread
2026-07-01 | Elk Solar — camera Reports (Aderis Acuity, x2) | Auto / Report | Automated report delivery | Open thread
2026-07-01 | aderis FOCUS — account validation code | Auth | Portal auth | Open thread
2026-07-01 | Colorado SoS — Periodic Report filed (Korsolis LLC) | Admin | Entity filing confirmation | Open thread
2026-06-30 | Microsoft/SharePoint — 'large number of files deleted' notice | Admin | OneDrive deletion notice (confirms old working folder removed) | Open thread
2026-06-30 | Diverxia — EPC availability in the US | Vendor | EPC sales solicitation | Open thread
2026-06-30 | SolRiver internal — Abhinav/SolRiver call invites (Wed 7/1) | Notification | Internal calendar | Open thread